## Table 1
Sprint Backlog
| Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26
| 1 |  | Sprint Plan Meeting | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
| 1, 1 |  | Create Sprint Backlog for Sprint | All member | Done | 10 | 10 | 0 | 10 | 0 | Day 1: 10
| 1, 2 |  | Create Test Plan for Sprint 3 | Manh, Vy, Quan | Done | 10 | 10 | 0 | 10 | 0 | Day 2: 10
| 1, 3 | PB09 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 3: 5
| 1, 4 | PB09 | Design Database | Lich | Done | 10 | 10 | 0 | 10 | 0 | Day 3: 10
| 1, 5 | PB09 | Code BE | Kien | Done | 35 | 35 | 0 | 38 | 3 | Day 13: 35
| 1, 6 | PB09 | Code FE | Manh, Vy | Done | 30 | 30 | 0 | 35 | 5 | Day 10: 30
| 1, 7 | PB09 | Test & fix bug | All | Done | 5 | 5 | 0 | 8 | 3 | Day 14: 5
| 1, 8 | PB18 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 4: 5
| 1, 9 | PB18 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 4: 5
| 1, 10 | PB18 | Code BE | Kien | Done | 25 | 25 | 0 | 30 | 5 | Day 16: 25
| 1, 11 | PB18 | Code FE | Manh, Vy | Done | 25 | 25 | 0 | 30 | 5 | Day 14: 25
| 1, 12 | PB18 | Test & fix bug | All | Done | 5 | 5 | 0 | 8 | 3 | Day 22: 5
| 1, 13 | PB20 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 5: 5
| 1, 14 | PB20 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 4: 5
| 1, 15 | PB20 | Code BE | Kien | Done | 15 | 15 | 0 | 17 | 2 | Day 8: 15
| 1, 16 | PB20 | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 16 | 1 | Day 9: 10
| 1, 17 | PB20 | Test & fix bug | All | Done | 5 | 5 | 0 | 8 | 3 | Day 10: 5
| 1, 18 | PB24 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 6: 5
| 1, 19 | PB24 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 5: 5
| 1, 20 | PB24 | Code BE | Kien | Done | 25 | 25 | 0 | 28 | 3 | Day 5: 25
| 1, 21 | PB24 | Code FE | Manh, Vy | Done | 25 | 25 | 0 | 28 | 3 | Day 12: 25
| 1, 22 | PB24 | Test & fix bug | All | Done | 5 | 5 | 0 | 8 | 3 | Day 13: 5
| 1, 23 | PB10 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 8 | 3 | Day 6: 5
| 1, 24 | PB10 | Design Database | Lich | Done | 10 | 10 | 0 | 10 | 0 | Day 7: 10
| 1, 25 | PB10 | Code BE | Kien | Overtimed | 30 | 30 | 0 | 35 | 5 | Day 26: 25
| 1, 26 | PB10 | Code FE | Manh, Vy | Done | 25 | 25 | 0 | 30 | 5 | Day 15: 25
| 1, 27 | PB10 | Test & fix bug | All | Overtimed | 5 | 5 | 0 | 8 | 3 | Day 26: 5
| 1, 28 | PB12 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 7 | 2 | Day 7: 5
| 1, 29 | PB12 | Code BE | Kien | Done | 15 | 15 | 0 | 18 | 3 | Day 17: 15
| 1, 30 | PB12 | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 10 | 0 | Day 18: 10
| 1, 31 | PB12 | Test & fix bug | All | Done | 5 | 5 | 0 | 8 | 3 | Day 22: 5
| 1, 32 | PB11 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 8 | 3 | Day 7: 5
| 1, 33 | PB11 | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 20 | 10 | Day 26: 8
| 1, 34 | PB11 | Test & fix bug | All | Overtimed | 5 | 5 | 0 | 10 | 5 | Day 26: 3
| 1, 35 |  | Sprint review | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
| 1, 36 |  | Sprint retrospective | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
| 1, 37 |  | Release & Closing | All member | Done | 2 | 2 | 0 | 2 | 0 | Day 26: 2
[5 empty] | Total | 424 | 424 | 0 | 509 | 85 | 14 | 10 | 15 | 15 | 35 | 10 | 20 | 15 | 10 | 35 | 0 | 25 | 40 | 30 | 25 | 25 | 15 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 51
[5 empty] | Burn down | [5 empty] | 410 | 400 | 385 | 370 | 335 | 325 | 305 | 290 | 280 | 245 | 245 | 220 | 180 | 150 | 125 | 100 | 85 | 75 | 75 | 75 | 75 | 65 | 65 | 65 | 65 | 14
[5 empty] | Burn up | [5 empty] | 14 | 24 | 39 | 54 | 89 | 99 | 119 | 134 | 144 | 179 | 179 | 204 | 244 | 274 | 299 | 324 | 339 | 349 | 349 | 349 | 349 | 359 | 359 | 359 | 359 | 410
[9 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Total hours
[9 empty] | Kien |  | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 6 | 4 | 4 | 3 | 3 | 3 | 6 | 3 | 3 | 4 | 4 | 4 | 5 | 3 | 6 | 6 | 4 | 4 | 4 | 100
[9 empty] | Lich |  | 4 | 4 | 4 | 4 | 3 | 4 | 2 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 94
[9 empty] | Quan |  | 4 |  | 4 | 4 | 3 | 4 | 2 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3 | 4 | 4 | 4 | 5 | 3 | 4 | 4 | 4 | 4 | 5 | 92
[9 empty] | Vy |  | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 90
[9 empty] | Manh |  | 4 | 4 | 4 | 3 | 4 | 3 | 2 | 3 | 4 | 4 | 3 | 4 | 2 | 3 | 5 | 4 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 95
471
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
410 400 385 370
335 325
305 290 280
245 245 220
180
150 125
100 85 75 75 75 75 65 65 65 65
14
Burn Down Chart
450
400
350
300
250
200
150
100
50
0
Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26