## Table 1
Sprint Backlog
| Sprint Id | Backlog Id |  | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26
| 1 |  |  | Sprint Plan Meeting | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
| 1, 1 |  |  | Create Sprint Backlog for Sprint | All member | Done | 10 | 10 | 0 | 10 | 0 | Day 1: 10
| 1, 2 |  |  | Create Test Plan for Sprint 2 | Manh, Vy, Quan | Done | 10 | 10 | 0 | 10 | 0 | Day 2: 10
| 1, 3 | PB03 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 3: 5
| 1, 4 | PB03 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 3: 5
| 1, 5 | PB03 |  | Code BE | Kien | Done | 20 | 20 | 0 | 21 | 1 | Day 11: 20
| 1, 6 | PB03 |  | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 15 | 0 | Day 10: 15
| 1, 7 | PB03 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 8 | 5 | Day 12: 3
| 1, 8 | PB08 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 3: 5
| 1, 9 | PB08 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 3: 5
| 1, 10 | PB08 |  | Code BE | Kien | Done | 15 | 15 | 0 | 17 | 2 | Day 15: 20
| 1, 11 | PB08 |  | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 12 | 2 | Day 12: 10
| 1, 12 | PB08 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 8 | 5 | Day 16: 3
| 1, 13 | PB07 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 4: 5
| 1, 14 | PB07 |  | Code BE | Kien | Done | 15 | 15 | 0 | 15 | 0 | Day 13: 15
| 1, 15 | PB07 |  | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 10 | 0 | Day 14: 10
| 1, 16 | PB07 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 8 | 5 | Day 15: 3
| 1, 17 | PB17 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 4: 5
| 1, 18 | PB17 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 4: 5
| 1, 19 | PB17 |  | Code BE | Kien | Overtimed | 20 | 20 | 0 | 25 | 5 | Day 26: 17
| 1, 20 | PB17 |  | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 15 | 0 | Day 16: 15
| 1, 21 | PB17 |  | Test & fix bug | All | Overtimed | 3 | 3 | 0 | 5 | 2 | Day 26: 2
| 1, 22 | PB13 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 5: 5
| 1, 23 | PB13 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 5: 5
| 1, 24 | PB13 |  | Code BE | Lich | Done | 25 | 25 | 0 | 30 | 5 | Day 8: 25
| 1, 25 | PB13 |  | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 20 | 5 | Day 8: 15
| 1, 26 | PB13 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 8 | 5 | Day 9: 5
| 1, 27 | PB15 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 5 | 0 | Day 6: 5
| 1, 28 | PB15 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 6: 5
| 1, 29 | PB15 |  | Code BE | Quan, Kien | Done | 10 | 10 | 0 | 16 | 6 | Day 17: 10
| 1, 30 | PB15 |  | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 16 | 6 | Day 18: 10
| 1, 31 | PB15 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 8 | 5 | Day 18: 3
| 1, 32 | PB16 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 7: 5
| 1, 33 | PB16 |  | Code BE | Lich | Done | 25 | 25 | 0 | 25 | 0
| 1, 34 | PB16 |  | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 15 | 0 | Day 20: 15
| 1, 35 | PB16 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 3 | 0
| 1, 36 | PB21 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 8: 5
| 1, 37 | PB21 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 8: 5
| 1, 38 | PB21 |  | Code BE | Kien | Done | 15 | 15 | 0 | 16 | 1 | Day 21: 15
| 1, 39 | PB21 |  | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 11 | 1 | Day 22: 10
| 1, 40 | PB21 |  | Test & fix bug | All | Done | 3 | 3 | 0 | 3 | 0 | Day 23: 3
| 1, 41 | PB23 |  | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 9: 5
| 1, 42 | PB23 |  | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 9: 5
| 1, 43 | PB23 |  | Code BE | Kien | Overtimed | 20 | 20 | 0 | 25 | 5 | Day 26: 15
| 1, 44 | PB23 |  | Code FE | Manh, Vy | Overtimed | 15 | 15 | 0 | 20 | 5 | Day 26: 10
| 1, 45 | PB23 |  | Test & fix bug | All | Overtimed | 3 | 3 | 0 | 5 | 2 | Day 26: 3
| 1, 46 |  |  | Sprint review | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
| 1, 47 |  |  | Sprint retrospective | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
| 1, 48 |  |  | Release & Closing | All member | Done | 2 | 2 | 0 | 2 | 0 | Day 26: 2
[6 empty] | Total | 421 | 421 | 0 | 502 | 81 | 14 | 10 | 20 | 15 | 10 | 10 | 5 | 50 | 15 | 15 | 20 | 13 | 15 | 10 | 23 | 18 | 10 | 13 | 0 | 15 | 15 | 10 | 3 | 0 | 0 | 57
[6 empty] | Burn down | [5 empty] | 407 | 397 | 377 | 362 | 352 | 342 | 337 | 287 | 272 | 257 | 237 | 224 | 209 | 199 | 176 | 158 | 148 | 135 | 135 | 120 | 105 | 95 | 92 | 92 | 92 | 35
[6 empty] | Burn up | [5 empty] | 14 | 24 | 44 | 59 | 69 | 79 | 84 | 134 | 149 | 164 | 184 | 197 | 212 | 222 | 245 | 263 | 273 | 286 | 286 | 301 | 316 | 326 | 329 | 329 | 329 | 386
[10 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Total hours
[10 empty] | Kien |  | 4 | 4 | 4 | 3 | 5 | 5 | 5 | 6 | 4 | 4 | 3 | 3 | 3 | 6 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 6 | 6 | 4 | 4 | 4 | 111
[10 empty] | Lich |  | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 100
[10 empty] | Quan |  | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 101
[10 empty] | Vy |  | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 90
[10 empty] | Manh |  | 4 | 4 | 4 | 3 | 4 | 3 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 4 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 100
502
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
407 397 377 362 352
342 337
287 272 257
237 224 209 199
176 158
148 135 135 120 105
95 92 92 92
35
Burn Down Chart
450
400
350
300
250
200
150
100
50
0
Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26