International School

# CAPSTONE PROJECT 1

CMU-SE 450

PROJECT PLAN DOCUMENT

Clinic Booking

Clinic Booking and Management System using Chatbot and Voice Assistant

# Submitted by: C1SE.62

Project Plan Review Panel Representative:

Name:	Signature	Date

# Capstone Project 1- Mentor:

Name: Msc.Nguyen Trung Thuan	Signature	Date

REVISION HISTORY

| Version | Date | Comments | Author | Approval |
| --- | --- | --- | --- | --- |
| 1.0 | 20/09/2024 | Initial Release | Tran, Trung Kien |  |

PROJECT INFORMATION

| Project acronym | CB |  |  |
| --- | --- | --- | --- |
| Project Title | Clinic Booking |  |  |
| Start Date | September 6, 2024 | End Date | December 20, 2024 |
| Lead Institution | International School, Duy Tan University |  |  |
| Project Mentor | Msc.Nguyen Trung Thuan |  |  |
| Scrum master / Project Leader & contact details | Doan Hoang Quan Email: quandoan.140203@gmail.com Tel: 0905413819 ID: 27211242264 |  |  |
| Partner Organization | Duy Tan University |  |  |
| Project Web URL |  |  |  |
| Team members | Name | Email | Tel |
| 27211248324 | Manh, Vo Van | vanmanh23012003@gmail.com | 0905118140 |
| 27211242264 | Quan, Doan Hoang | quandoan.140203@gmail.com | 0905413819 |
| 27211201526 | Lich, Huynh Ngoc | huynhngoclich10052003@gmail.com | 0935513362 |
| 26201241995 | Vy, Nguyen Yen | vyzit112002@gmail.com | 0775513141 |
| 27211221365 | Kien, Tran Trung | trantrungkien6@dtu.edu.vn | 0368313577 |

DOCUMENT NAME

| Document Title | Project Plan Document |  |  |
| --- | --- | --- | --- |
| Reporting Period |  |  |  |
| Author(s) | Tran, Trung Kien |  |  |
| Role | Developer |  |  |
| Date | 20/09/2023 | Filename | C1SE.62-PROJECT- PLAN_ClinicBooking-V1.0 |

Document Approval

The following signatures are required for approval of this document.

| Mentor | Msc.Nguyen Trung Thuan | Signature: |  |
| --- | --- | --- | --- |
|  |  | Date: |  |
| Scrum Master | Quan, Doan Hoang | Signature: |  |
|  |  | Date: |  |
| Team Member(s) | Manh, Vo Van | Signature: |  |
|  |  | Date: |  |
|  | Lich, Huynh Ngoc | Signature: |  |
|  |  | Date: |  |
|  | Vy, Nguyen Yen | Signature: |  |
|  |  | Date: |  |
|  | Kien, Tran Trung | Signature: |  |
|  |  | Date: |  |

Table of Content

- PROJECT OVERVIEW	9

  - Project Description	9

  - Purpose and Scope	9

    - Purpose	9

    - Scope	10

  - Assumptions and Constraints	11

  - Project Objectives	12

    - Standard Objectives	13

    - Specific Objectives	13

  - Standard Objectives	14

  - Standard Objectives	14

- Project Development Approach	17

  - Technical Process	17

  - Reasons for selecting.	17

  - Agile Methodology	17

  - Scrum Process	20

  - Quality Management	20

  - Estimates of Defects to be detected	20

  - Strategy for Meeting Quality Objective	21

  - Quality Control	21

  - Measurements Program	22

  - Unit Testing Strategy	22

  - Integration Testing Strategy	22

- Estimation	24

  - Size	24

  - Effort	24

  - Schedule	24

    - Project Milestone & Deliverables	25

    - Work Breakdown Structure	25

    - All Member Detailed Schedule	25

    - Project Schedule	35

  - Resource	36

  - Infrastructure	36

  - Training Plan	36

- Project Organization	37

  - Organization Structure	38

  - Project Team	40

- Communication & Reporting	41

- Configuration Management	42

- Security Aspects	42

REFERENCES	43

# Figure

Figure 1. Agile project life cycle	19

Figure 2. Scrum process	20

Figure 3. Work BreakdownStructure	26

Table

Table 1: Project Description	9

Table 2: Assumptions and Constraints.	11

Table 3: Standard Objectives	12

Table 4: Critical Dependencies	13

Table 5: Project Risk	16

Table 6: Estimates of Defect	20

Table 7: Strategy for Meeting Quality Objective	21

Table 8 : Quality Control	21

Table 9: Measurements Program	22

Table 10: Integration Testing Strategy	23

Table 11: Size	24

Table 12: Project Milestone & Deliverables	25

Table 13: Detailed Schedule	38

Table 14: Project Schedule	40

Table 15: Resource	40

Table 16: Infrastructure	41

Table 17: Traning Plan	42

Table 18: Organization Structure	43

Table 19: Project Team	44

Table 20: Communication & Reporting	45

# PROJECT OVERVIEW

# Project Description

Table 1: Project Description

| Project code | Clinic Booking | Contract type |  |
| --- | --- | --- | --- |
| Customer | N/A | End-User | User, Doctor, Admin |
| Project Level | Group | Project rank | B |
| Group | Team SE62 | Division |  |
| Project Type | N/A | Project Manager/ Scrum master | Quan, Doan Hoang |
| Project Category | Development and Maintenance | Business domain | Service |
| Application type | Website |  |  |

# Purpose and Scope

# Purpose

- The purpose of this project is to develop a comprehensive Clinic Booking and Management System that enhances patient experience and clinic efficiency. The system will leverage the power of chatbots and voice assistants to streamline appointment scheduling, manage patient information, facilitate online consultations, and provide seamless integration with Electronic Health Records.

- Key objectives:

  - Convenient Appointment Scheduling: Provide patients with a fast and easy way to book appointments online through a user-friendly interface and chatbot interaction.

  - Enhanced Patient Management: Enable efficient management of patient information, including personal details, medical history, prescriptions, and Electronic Health Records.

  - Improved Doctor-Patient Communication: Facilitate online consultations between patients and doctors using AI chatbot technology, allowing for real-time information exchange and virtual consultations.

  - Streamlined Clinic Operations: Optimize clinic management by providing tools for doctors to efficiently manage schedules, view patient records, update medical information, and evaluate patient care.

  - Secure Data Management: Implement robust security measures to protect patient data privacy and ensure secure data storage.

# Scope

- This document outlines the key aspects of the project plan, detailing the scope of work, major milestones, resource allocation, project timeline, and budget allocation. The plan is based on the project proposal and aims to guide the development team in building a comprehensive and user-friendly clinic management system within the designated time frame.

# The Clinic Booking system will comprise the following features:

  - Web Application Development: Building a responsive web platform accessible to patients, doctors, and administrators.

  - AI Chatbot and Voice Assistant Integration: Implementing a sophisticated AI Chatbot with natural language processing (NLP) capabilities for online consultation and appointment scheduling, and a Voice Assistant for seamless integration with Electronic Health Records.

  - Secure Database Management: Establishing a secure database to store patient information, appointments, Electronic Health Records, and prescriptions, ensuring data privacy and integrity.

  - User Management System: Implementing user accounts for patients, doctors, and administrators, enabling registration, profile management, and access control.

  - Appointment Scheduling System: Providing a user-friendly interface for appointment booking, cancellation, and rescheduling.

  - Electronic Health Records (EHR) Integration: Integrating with existing EHR systems for seamless data exchange and efficient record management.

  - Doctor Evaluation System: Allowing patients to provide feedback on doctor performance and service quality.

  - Automated Reminders and Notifications: Delivering timely notifications to patients and doctors via SMS, email, or in-app messages.

  - Billing and Payments: Implementing a secure and convenient online payment system for clinic services.

  - Reporting and Analytics: Providing insightful reports and analytics for clinic performance and resource management.

⮚

# Assumptions and Constraints.

Table 2: Assumptions and Constraints.

| No | Description | Note |
| --- | --- | --- |
| Assumptions |  |  |
| 1 | There is a new feature in the project development life cycle that may arise. | Scope |
| 2 | Documentation changes are required by the stakeholder. | External Interfaces |
| 3 | There is a shortage of human resources while developing the project. | Resources |
| 4 | The project cannot meet All Member requirements. | Quality |
| 5 | Project development time can be extended or shortened by 1 week. | Schedule |
| Constraints |  |  |
| 1 | The project must meet All Member requirements in the User Story. | Schedule |
| 2 | The project shall conform to security requirements specified by the customer in the NDA | Security |
| 3 | The product operates at a high level of performance and has a page load of no more than 5 seconds. | Quality |
| 4 | The application operates in a website | Scope |
| 5 | The project will be implemented by a team including 5 members | Resources |
| 6 | The financial estimation for the project is at a budget limit of $4700 | Budget |

# Project Objectives

# Standard Objectives

Table 3: Standard Objectives

| Metrics | Unit | Committed | Note |
| --- | --- | --- | --- |
| Start Date | dd-mmm-yy | 6-Sep-24 |  |
| End Date | dd-mmm-yy | 15-Dec-24 |  |
| Duration | Elapsed days | 100 |  |
| Maximum Team Size | Person | 5 |  |
| Billable Effort | Person-day | 8 |  |
| Number of work hours per day for one engineer | Person-hour | 8 |  |

# Specific Objectives

- The project aims to build a user-friendly and efficient Clinic Booking & Management System with the following features:

  - Appointment Scheduler: Develop a user-friendly appointment scheduler allowing patients to easily book appointments online based on their preferred doctor, date, and time, considering doctor availability and clinic scheduling rules.

  - User Management: Implement a comprehensive user management system to effectively manage user accounts, profiles, and permissions for patients, doctors, and administrators. This includes secure registration, profile editing, access control, and role-based access.

  - Patient Information Management: Establish a robust system to securely store and manage patient information, including personal details, medical history, prescriptions, and Electronic Health Records. The system should ensure data integrity, privacy, and accessibility for authorized personnel.

  - AI Chatbot & Voice Assistant Integration: Implement a conversational AI chatbot and a Voice Assistant to enhance user experience. The chatbot will provide patients with information about the clinic, services, doctors, and appointment scheduling, while the Voice Assistant allows patients to interact

with the system using voice commands.

  - Online Consultations: Enable online consultations between patients and doctors through AI chatbot technology, facilitating virtual communication and allowing patients to receive medical advice and guidance remotely.

  - Electronic Health Records (EHR) Integration: Integrate with existing Electronic Health Record systems to seamlessly pull relevant data and ensure accurate billing and patient record management, ensuring security and compliance with data privacy regulations.

  - Doctor Management: Develop a user-friendly dashboard for doctors to efficiently manage their schedules, view patient records, update medical information, and receive patient feedback.

  - Clinic Management: Provide administrators with a comprehensive management system for managing user accounts, clinic resources, billing and payments, and generating reports on clinic performance and operational insights.

  - Security & Privacy: Implement robust security measures to protect patient data, ensuring compliance with data privacy regulations. The system should be secure against unauthorized access, data breaches, and other cyber threats.

  - Automated Reminders and Notifications: Develop a notification system that sends timely reminders and alerts to patients and doctors regarding appointments, consultations, and important updates.

  - Reporting and Analytics: Provide administrators with tools for generating comprehensive reports and analytics on clinic performance, appointment trends, patient demographics, and resource utilization.

# Standard Objectives

Table 4: Critical Dependencies

| No | Dependency | Expected delivery date | Note |
| --- | --- | --- | --- |
| 1 | N/A | N/A |  |
| 2 | N/A | N/A |  |
| 3 | N/A | N/A |  |

# Standard Objectives

Table 5: Project Risk

| ID | Identify Risk | Descriptions | Probability | Impact | Priority | Mitigations | Remedy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Scope definition | The scope of the project may change during development, or there may be redundant or unnecessary features included in the scope. | 50% | 4 | 2 | The project scope should be clearly defined and documented at the outset of the project, and any changes to the scope should be carefully considered and approved before they are implemente d. | Define project scope clearly at the start. Establish a process for handling scope changes with formal approvals. |
| 2 | Requirem ents definition | The requirements for the website may be incomplete, inconsistent, or ambiguous. | 30% | 4 | 1.2 | The requirement s for the website should be gathered and documented carefully, and they should be reviewed and approved by | Conduct thorough requirements- gathering sessions with stakeholders. Adopt agile methodology, so requirements can be refined throughout the project. |

|  |  |  |  |  |  | All Member stakeholders before developmen t begins. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | Resource s | The project may not have the necessary resources, such as staff, time, or funding, to complete the project on time and within budget. | 30% | 2 | 0.6 | The project should carefully estimate the resources required to complete the project, and it should develop a contingency plan in case of unforeseen resource shortages. | Create a detailed resource plan including staff allocation, budget, and timeline. Conduct regular project reviews to assess resource availability. |
| 4 | Communicat ion | There may be communicatio n problems between the project team members, the client, or other stakeholders. | 40% | 3 | 1.2 | The project team should establish clear communicat ion channels and procedures, and they should make sure to communicat e regularly with All | Set up regular communication routines, such as weekly team meetings or status updates. Use collaboration tools like Slack, Trello, or Zalo for real-time communication and project tracking. |

|  |  |  |  |  |  | Member stakeholders . |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Health | A team member may become ill or injured, which could delay the project. | 30% | 3 | 1.2 | The project should have a contingency plan in place in case of a team member's illness or injury. | Build slack time into the project timeline to accommodate unexpected delays. Encourage team members to document their work thoroughly for easy transition. |
| 6 | Time | The project may not be completed on time due to unforeseen delays. | 30% | 4 | 1.2 | The project should develop a realistic timeline and schedule, and it should be prepared to adjust the schedule as needed. | Use past project data and break down tasks into smaller components for more accurate time and cost estimates. Build a 10-20% contingency into the budget for unforeseen expenses. |
| 7 | Estimate | The size of the project may be underestimate d, which could lead to budget overruns. | 60% | 4 | 2.4 | The project should carefully estimate the size of the project, and it should develop a | Regularly compare the actual project progress against the estimates and adjust the scope, budget, |

|  |  |  |  |  |  | contingency plan in case of unforeseen cost increases. | or timeline as necessary to avoid overruns. |
| --- | --- | --- | --- | --- | --- | --- | --- |

# Project Development Approach

# Technical Process

- We use agile methodology in our project, besides using software tools to manage work and assign tasks to team members such as Trello, Google Drive, Zalo, Discord, and Source code management tools like Git.

# Reasons for selecting.

  - Because we can be flexible with our changing requirements. During project development, that keeps our project running smoothly without interruption.

  - This is the first time the team has worked together, the experience is not much, and it will certainly be difficult in the development process. For the traditional model, we are not owed to make mistakes but our scrum, it owes us to make mistakes, through each sprint we will discuss, inspect and adapt to work better.

  - The scrum process is a flexible development model so in this case, it is suitable for this project.

# Agile Methodology

  - Agile methodology is a project management approach that emphasizes flexibility, collaboration, and iterative development. It divides projects into smaller phases and guides teams through cycles of planning, execution, and evaluation. Where demands and solutions evolve through the collaborative effort of self-organizing and cross-functional teams and their customers.

# Definition

  - "Agile methodology refers to a set of principles and practices for software development and project management that prioritize flexibility, collaboration, customer feedback, and iterative progress. It is an approach that aims to deliver high-quality products or services in a more responsive and adaptive manner compared to traditional, linear project management methods. Instead of betting everything on a 'big bang' launch, an agile team delivers work in small, consumable increments."

# Process

- Concept

This is the initial stage of the project, where the team defines the problem that the project is trying to solve and identifies the requirements for the solution.

- Inception

Team members are identified, finalize the requirements and creates a plan for the project. The team also starts to develop the software in this stage.

- Iteration/Construction

The team develops the software in an iterative and incremental way. The team delivers working software frequently to the customer for feedback.

- Release

The team continues to make changes to the software after it is released, but the focus is on supporting the customer and fixing any bugs that are found.

- Production

Maintaining the software and ensuring that it is working properly.

- Retirement

End-of-life activities, including customer notification and migration.

# Manifesto

  - The Agile Manifesto is a statement of core values and principles for software development. The Agile Manifesto for software development was set up in 2001 and it is a declaration of 4 vital rules and 12 principles that serve as a guide for people in agile software development. It was created by 17 professionals who already practiced agile methods such as XP, DSDM, SCRUM, FDD, etc, gathered in the snowy mountains of the US state of Utah, convened by Kent Beck.

# The Four Core Values of the Agile Manifesto:

  - Individuals and interactions over processes and tools.

  - Working software over comprehensive documentation.

  - Customer collaboration over contract negotiation.

  - Responding to change over following a plan.

# 12 Principles of the Agile Manifesto

- Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference for a shorter timescale.

- Businesspeople and developers must work together daily throughout the project.

- Build projects around motivated individuals. Give them the environment and

support they need and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.

- Working software is the primary measure of progress.

- Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhances agility.

- Simplicity–the art of maximizing the amount of work not done–is essential.

- The best architectures, requirements, and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

# Describe the Agile project life cycle:

Figure 1. Agile project life cycle.

  - Requirements: This is the initial stage of the project, where the team defines the problem that the project is trying to solve and identifies the requirements for the solution. The team works with the customer to gather requirements and to ensure that they are clear and well-defined.

  - Design: This stage is where the team creates a design for the solution. The design should be based on the requirements and should consider the constraints of the project, such as the budget and the timeline.

  - Development: This stage is where the team develops the solution. The team works in short cycles, or iterations, and delivers working software frequently to the customer for feedback.

  - Testing: This stage is where the team tests the solution to ensure that it meets

the requirements and is free of bugs. The team uses a variety of testing techniques, such as unit testing, integration testing, and system testing.

  - Deployment: This stage is where the solution is released to the customer. The team may also provide training to the customer on how to use the solution.

  - Review: This stage is where the team reviews the project and identifies any areas for improvement. The team may also gather feedback from the customer to help them improve the solution in future iterations.

# Scrum Process

Figure 2. Scrum process.

# Quality Management

# Estimates of Defects to be detected

Table 6: Estimates of Defect

| Process | Planned found by review |
| --- | --- |
| Requirement | 50 |
| Design | 30 |
| Coding | 180 |
| Other | 40 |
| Total | 300 |

# Strategy for Meeting Quality Objective

Table 7: Strategy for Meeting Quality Objective

| Strategy | Expected Benefits |
| --- | --- |
| - Use interactive user interface (UI/UX) design principles. - Create a UI test plan using manual testing techniques. | Ensuring a user-friendly and easy-to-use experience. |
| - Set key performance metrics like page load time and server response time. | Ensuring good system performance. |
| - Collect feedback from users and development team members for each functionality. | Improve functional quality. |

# Quality Control

Table 8 : Quality Control

| Review Item | Type of Review | Reviewer | When |
| --- | --- | --- | --- |
| Proposal | Group review | Mentor | Initial |
| Project Plan | Group review | Mentor | End of 90% of Initiation Stage |
| Project Schedule | Group reiew | Mentor |  |
| Product Backlog, User Story | Group review | Mentor | End of 90% of Requirements |
| Design Document | Group review | Mentor | End of 90% of Design |
| Sprint Backlog | Group review | Scrum master | Beginning of Each Sprint |
| Test case | One-person review | Product Owner | End of Detailed Design |

| Code | Group review | Mentor | After Coding For The First Few Programs |
| --- | --- | --- | --- |

# Measurements Program

Table 9: Measurements Program

| Data to be collected | Purpose | Responsible | When |
| --- | --- | --- | --- |
| Size: No. of KLOC//FP | Manage the size of the product. | PM/SM | At the end of stages |
| Effort: No. person- day | Estimation, evaluate member’s productivity. | Team Members | Daily |
| Quality: No. defects detected | Evaluate and improve the quality of the product | Team Members | Right after the test |
| Schedule | Control schedule, assign appropriate tasks | PM/SM | Weekly and at the end of stages |

# Unit Testing Strategy

# Integration Testing Strategy

Table 10: Integration Testing Strategy

| Components Need To Be Tested | Create Test Data | Acceptance Standards | Test Schedule |
| --- | --- | --- | --- |
| Registration | Create simulated data for registered accounts with different types of information. | The success of account registration. | After completion and after each update. |
| Login | Generate valid and invalid login account data. | Ability to log in successfully and handle errors when login fails. | After completion and after each update. |
| View User and Doctor Information | Create a user/ doctor list to view information. | Displays accurate user/ doctor information | After completion and after each update. |

| Set schedule | Create doctor’s schedule data with different scenarios. | Ability to schedule and troubleshoot errors when problems arise. | After completion and after each update. |
| --- | --- | --- | --- |
| Confirm booking payment | Create a mock checkout page | The success of checking the receipt from both parties | After completion and after each update. |

# System Testing Strategy

- Function:

  - Register and log in: Ensure users can register and log in successfully and securely.

  - Schedule:	Check	out	appointment	scheduling	features	including	booking, confirmation and cancellation.

- Efficiency:

  - Page load time: Determine the average page load time for the main pages of your website and ensure that it is within an acceptable range.

  - Capacity: Evaluates the system's ability to handle a number of concurrent users without causing overload.

- Security:

  - Check website security to ensure that there are no serious security vulnerabilities.

  - Authentication and authorization: Check the correctness of the user authentication and authorization management system.

- Compatibility:

  - Make sure the website works well on popular browsers like Chrome, CocCoc, Safari, and Edge.

- Integration and Systems:

  - Ensure integrations related to pre-integrated functionality such as registration and login work properly and do not cause conflicts.

  - Verify that the system can integrate with external databases and applications stably.

- Response Speed:

- Make sure the system response time when users interact with the website is good and does not cause discomfort.

- Resilience:

  - Test your system's ability to recover after a crash or error.

- Ability of Extension:

  - Ensure that the system is scalable to accommodate increased future needs.

- Stability:

  - Test over system stability by running test scripts continuously over a long period of time.

# Estimation

# Size

Table 11: Size

| Software Scale Drivers |  |
| --- | --- |
| Precedence | Nominal |
| Development Flexibility | Nominal |
| Architecture / Risk Resolution | Nominal |
| Team Cohesion | Very High |
| Process Maturity | Nominal |

# Effort

- Resources:

  - Total members: 5

  - Frontend (React JS): 3

    - Time: 100 Days

    - Estimated Cost: $1680

  - Backend (SpringBoot and MySQL): 2

    - Time: 100 Days

    - Estimated Cost: $1120

  - Software / Licenses:

  - React JS and UI Library (Material-UI):

    - Estimated Cost: $0 (Free for Using)

  - SpringBoot and MySQL:

    - Estimated Cost: $0 (Free for Using)

  - AI Chatbot API (ChatGPT or Gemini) and Voice Assistant API (Google):

    - Estimated Cost: $50

  - Hardware:

  - Servers and Storage:

    - Estimated Cost: $50 (Making Use of Low-Cost Cloud Server Services).

  - Other Relevant Expenses:

  - Costs of Development and Testing:

    - Estimated Cost: $15

  - Emergency Funds and Expenses:

    - Estimated Cost: $35

  - Post-deployment maintenance:

    - Estimated Cost: $880 per month

  - Risks in software projects (Technical Risks, Personnel Risks, Time Risks, Change Requirement Risks …):

    - Estimated Cost: $766 (20% of the project)

- Project Total: $4596

# Schedule

# Project Milestone & Deliverables

Table 12: Project Milestone & Deliverables

| No | Milestone | Time | Product |
| --- | --- | --- | --- |
| 1 | Initial | 06/09/2024 | The proposal, User Story, User Interface, Product Backlog, Project Plan, Architecture Document |
| 2 | Development | 28/09/2024 | Database Design |
| 2.1 | Sprint 1 | 28/09/2024 | Test Plan Test Case Sprint Backlog Product Backlog |
| 2.2 | Sprint 2 | 24/10/2024 |  |
| 2.3 | Sprint 3 | 19/11/2024 |  |
| 3 | Project Meeting | 14/12/2024 | Meeting Document |
| 4 | Final Release | 15/12/2024 | Reflection Document |

# Work Breakdown Structure

Figure 3. Work Breakdown Structure

# All Member Detailed Schedule

Table 13: Detailed Schedule

| No | Task Name | Duration (Days) | Start | Finish | Member |
| --- | --- | --- | --- | --- | --- |
| 1 | Initial | 7 | 03/9/2024 | 16/9/2024 | All Member |
| 1.1 | Create Proposal Document | 2 | 03/09/2024 | 04/09/2024 | All Member |

| 1.2 | Project Kick-off Meeting | 1 | 05/09/2024 | 05/09/2024 | All Member |
| --- | --- | --- | --- | --- | --- |
| 1.3 | Discuss project idea | 2 | 06/09/2024 | 07/09/2024 | All Member |
| 1.4 | Update Proposal Document | 2 | 08/09/2024 | 10/09/2024 | All Member |
| 1.1 | Create Document | 17 | 11/09/2024 | 27/09/2024 | All Member |
| 1.1.1 | Create Project Plan | 3 | 11/09/2024 | 13/09/2024 | All Member |
| 1.1.2 | Create Product Backlog | 3 | 14/09/2024 | 16/09/2024 | Quan, Kien |
| 1.1.3 | Create User Story | 2 | 17/09/2024 | 18/09/2023 | Vy |
| 1.1.4 | Create User Interface | 2 | 19/09/2024 | 20/09/2024 | Vy, Manh, Lich |
| 1.1.5 | Create Database Document | 3 | 21/09/2024 | 23/09/2024 | Quan, Kien |
| 1.1.6 | Create Architecture Document | 3 | 24/09/2024 | 26/09/2024 | All Member |
| 1.1.7 | Review Document | 1 | 27/09/2024 | 27/09/2024 | All Member |
| 2 | Development | 77 | 28/09/2024 | 13/12/2024 | All Member |
| 2.1 | Sprint 1 | 26 | 28/09/2024 | 23/10/2024 | All Member |
| 2.1.1 | Initial Sprint 1 | 2 | 28/09/2024 | 29/09/2024 | All Member |
| 2.1.1.1 | Sprint Planning Meeting | 1 | 28/09/2024 | 28/09/2024 | All Member |
| 2.1.1.2 | Create Sprint backlog for Sprint 1 | 1 | 29/09/2024 | 29/09/2024 | Quan |
| 2.1.1.3 | Create Test Plan Document for Sprint 1 | 1 | 29/09/2024 | 29/09/2024 | Vy |

| 2.1.1.4 | Create Database Document Sprint 1 | 1 | 29/09/2024 | 29/09/2024 | Kien |
| --- | --- | --- | --- | --- | --- |
| 2.1.2 | Design UI | 2 | 30/09/2024 | 2/10/2024 | Lich, Vy, Manh |
| 2.1.2.1 | Design UI [User] Login/Logout | 1 | 30/09/2024 | 30/09/2024 | Manh |
| 2.1.2.2 | Design UI [User] Register | 1 | 01/10/2024 | 01/10/2024 | Manh |
| 2.1.2.3 | Design UI [User] Forgot password | 1 | 01/10/2024 | 01/10/2024 | Manh |
| 2.1.2.4 | Design UI [User] Homepage | 1 | 01/10/2024 | 01/10/2024 | Quan |
| 2.1.2.5 | Design UI [Admin] Admin Page | 1 | 30/09/2024 | 30/09/2024 | Lich |
| 2.1.2.6 | Design UI [Admin] Information User & Doctor | 1 | 01/10/2024 | 01/10/2024 | Lich |
| 2.1.2.7 | Design UI [Doctor] Doctor Homepage | 1 | 30/09/2024 | 30/09/2024 | Vy |
| 2.1.2.8 | Design UI [Doctor] Doctor ‘s Working Schedule | 1 | 01/10/2024 | 01/10/2024 | Vy |
| 2.1.2.9 | Design UI [Doctor] Manage patient’s Electronic Health Records | 1 | 01/10/2024 | 01/10/2024 | Kien |
| 2.1.3 | Design Test Case | 2 | 02/10/2024 | 03/10/2024 | Vy |
| 2.1.4 | Code | 14 | 04/10/2024 | 17/10/2024 | All Member |

| 2.1.4.1 | Code Front-end [User] Login/ Logout | 2 | 04/10/2024 | 05/10/2024 | Manh |
| --- | --- | --- | --- | --- | --- |
| 2.1.4.2 | Code Front-end [User] Homepage | 2 | 06/10/2024 | 07/10/2024 | Vy |
| 2.1.4.3 | Code Front-end [User] Register | 2 | 08/10/2024 | 09/10/2024 | Manh |
| 2.1.4.4 | Code Front-end [User] Forgot password | 1 | 10/10/2024 | 10/10/2024 | Manh |
| 2.1.4.5 | Code Front-end [Admin] Information User & Doctor | 2 | 11/10/2024 | 12/10/2024 | Lich |
| 2.1. 4.6 | Code Front-end [Admin] Admin page | 2 | 13/10/2024 | 14/10/2024 | Lich |
| 2.1. 4.7 | Code Front-end [Doctor] Doctor Homepage | 2 | 12/10/2024 | 13/10/2024 | Vy |
| 2.1. 4.8 | Code Front-end [Doctor] Doctor ‘s Working Schedule | 4 | 15/10/2024 | 18/10/2024 | Lich |
| 2.1. 4.9 | Code Front-end [Doctor] Manage patient’s Electronic Health Records | 2 | 15/10/2024 | 16/10/2024 | Vy |
| 2.1.4.10 | Code Back-end [User] Login | 2 | 14/10/2024 | 15/10/2024 | Quan |
| 2.1.4.11 | Code Back-end [User] Logout | 1 | 16/10/2024 | 16/10/2024 | Quan |
| 2.1.4.12 | Code Back-end [User] Register | 1 | 17/10/2024 | 17/10/2024 | Quan |

| 2.1.4.13 | Code Back-end [User] Home Page | 2 | 15/10/2024 | 16/10/2024 | Kien |
| --- | --- | --- | --- | --- | --- |
| 2.1.4.14 | Code Back-end [Admin] Infomation User | 1 | 17/10/2024 | 17/10/2024 | Kien |
| 2.1.5 | Testing | 1 | 18/10/2024 | 18/10/2024 | All Member |
| 2.1.6 | Fix bugs | 2 | 19/10/2024 | 20/10/2024 | Duong |
| 2.1.7 | Re-testing | 1 | 21/10/2024 | 21/10/2024 | All Member |
| 2.1.8 | Release Sprint 1 | 2 | 22/10/2024 | 23/10/2024 | All Member |
| 2.1.8.1 | Sprint 1 Review Meeting | 1 | 22/10/2024 | 22/10/2024 | All Member |
| 2.1.8.2 | Sprint 1 Retrospective | 1 | 23/10/2024 | 23/10/2024 | All Member |
| 2.2 | Sprint 2 | 26 | 24/10/2024 | 18/11/2024 | All Member |
| 2.2.1 | Initial Sprint 2 | 2 | 24/10/2024 | 26/10/2024 | All Member |
| 2.2.1.1 | Sprint Planning Meeting | 1 | 24/10/2024 | 24/10/2024 | All Member |
| 2.2.1.2 | Create Sprint backlog for Sprint 2 | 1 | 25/10/2024 | 25/10/2024 | Quan |
| 2.2.1.3 | Create Test Plan Document for Sprint 2 | 1 | 26/10/2024 | 26/10/2024 | Vy |
| 2.2.1.4 | Create Database Document Sprint 2 | 1 | 26/10/2024 | 26/10/2024 | Kien |
| 2.2.2 | Design UI | 3 | 27/10/2024 | 29/10/2024 | Lich, Vy, Manh |

| 2.2.2.1 | Design UI [Admin] Admin Homepage | 1 | 27/10/2024 | 27/10/2024 | Lich |
| --- | --- | --- | --- | --- | --- |
| 2.2.2.2 | Design UI [Admin] Update Information User | 1 | 28/10/2024 | 28/10/2024 | Lich |
| 2.2.2.3 | Design UI [User] Booking | 1 | 28/10/2024 | 28/10/2024 | Vy |
| 2.2.2.4 | Design UI [User] Update Electronic Health Record | 1 | 27/10/2024 | 27/10/2024 | Manh |
| 2.2.2.5 | Design UI [User] Chatbot | 1 | 29/10/2024 | 29/10/2024 | Vy |
| 2.2.2.6 | Design UI [User] Rating and Feedback | 1 | 28/10/2024 | 28/10/2024 | Manh |
| 2.2.2.7 | Design UI [User] Report | 1 | 29/10/2024 | 29/10/2024 | Manh |
| 2.2.3 | Design Test Case | 2 | 30/10/2024 | 31/10/2024 | Vy |
| 2.2.4 | Code | 14 | 01/11/2024 | 14/11/2024 | All members |
| 2.2.4.1 | Code Front-end [Admin] Admin Homepage | 2 | 01/11/2024 | 02/11/2024 | Lich |
| 2.2.4.2 | Code Front-end [Admin] Update Information User | 2 | 03/11/2024 | 04/11/2024 | Lich |
| 2.2.4.3 | Code Front-end [User] Booking | 2 | 05/11/2024 | 06/11/2024 | Vy |
| 2.2.4.4 | Code Front-end [User] Doctor Information | 1 | 06/11/2024 | 06/11/2024 | Manh |

| 2.2.4.5 | Code Front-end [User] Chatbot | 1 | 07/11/2024 | 07/11/2024 | Vy |
| --- | --- | --- | --- | --- | --- |
| 2.2.4.6 | Code Front-end [User] Rating and Feedback | 2 | 07/11/2024 | 07/11/2024 | Manh |
| 2.2.4.7 | Code Front-end [User] Report | 1 | 08/11/2024 | 08/11/2024 | Manh |
| 2.2.4.8 | Code Back-end [User] Forgot password | 2 | 08/11/2024 | 09/11/2024 | Quan |
| 2.2.4.9 | Code Back-end [Admin] Information Doctor | 1 | 05/11/2024 | 05/11/2024 | Kien |
| 2.2.4.10 | Code Back-end [User] Booking | 2 | 06/11/2024 | 07/11/2024 | Kien |
| 2.2.4.11 | Code Back-end [User] Electronic Health Records | 2 | 08/11/2024 | 09/11/2024 | Kien |
| 2.2.4.12 | Code Back-end [User] Rating and Feedback | 2 | 10/11/2024 | 11/11/2024 | Kien |
| 2.2.4.13 | Code Back-end [User] Report | 1 | 12/11/2024 | 12/11/2024 | Kien |
| 2.2.5 | Testing | 1 | 13/11/2024 | 13/11/2024 | All Member |
| 2.2.6 | Fix bugs | 2 | 14/11/2024 | 15/11/2024 | All Member |
| 2.2.7 | Re-testing | 1 | 16/11/2024 | 16/11/2024 | All Member |
| 2.2.8 | Release Sprint 2 | 2 | 17/11/2024 | 18/11/2024 | All Member |

| 2.2.8.1 | Sprint 2 Review Meeting | 1 | 17/11/2024 | 17/11/2024 | All Member |
| --- | --- | --- | --- | --- | --- |
| 2.2.8.2 | Sprint 2 Retrospective | 1 | 18/11/2024 | 18/11/2024 | All Member |
| 2.3 | Sprint 3 | 25 | 19/11/2024 | 13/12/2024 | All Member |
| 2.3.1 | Initial Sprint 3 | 2 | 19/11/2024 | 20/11/2024 | All Member |
| 2.3.1.1 | Sprint Planning Meeting | 1 | 19/11/2024 | 19/11/2024 | All Member |
| 2.3.1.2 | Create Sprint backlog for Sprint 3 | 1 | 20/11/2024 | 20/11/2024 | Quan |
| 2.3.1.3 | Create Test Plan Document for Sprint 3 | 1 | 20/11/2024 | 20/11/2024 | Vy |
| 2.3.1.4 | Create Database Document Sprint 3 | 1 | 20/11/2024 | 20/11/2024 | Kien |
| 2.3.2 | Design UI | 3 | 21/11/2024 | 23/11/2024 | Lich, Vy, Manh |
| 2.3.2.1 | Design UI [Admin] Medicine Management | 1 | 21/11/2024 | 21/11/2024 | Lich |
| 2.3.2.2 | Design UI [User / Doctor] Voice Assistant | 1 | 21/11/2024 | 21/11/2024 | Vy |
| 2.3.2.3 | Design UI [User] Doctor Information | 1 | 21/11/2024 | 21/11/2024 | Manh |
| 2.3.2.4 | Design UI [User] Service Price List | 1 | 22/11/2024 | 22/11/2024 | Manh |

| 2.3.2.5 | Design UI [Doctor] Update Information Doctor | 1 | 22/11/2024 | 22/11/2024 | Vy |
| --- | --- | --- | --- | --- | --- |
| 2.3.2.6 | Design UI [User/ Admin] Booking History | 1 | 23/11/2024 | 23/11/2024 | Manh |
| 2.3.2.7 | Design UI [Doctor] Reply Rating and Feedback | 1 | 23/11/2024 | 23/11/2024 | Vy |
| 2.3.2.8 | Design UI [Doctor] Send Prescription to User | 1 | 23/11/2024 | 23/11/2024 | Vy |
| 2.3.3 | Design Test Case | 2 | 24/11/2024 | 25/11/2024 | Vy |
| 2.3.4 | Code | 12 | 26/11/2024 | 7/12/2024 | All member |
| 2.3.4.1 | Code Front-end [Admin] Medicine Management | 1 | 26/11/2024 | 26/11/2024 | Lich |
| 2.3.4.2 | Code Front-end [User / Doctor] Voice Assistant | 3 | 26/11/2024 | 28/11/2024 | Vy |
| 2.3.4.3 | Code Front-end [User] Doctor Information | 2 | 27/11/2024 | 28/11/2024 | Manh |
| 2.3.4.4 | Code Front-end [User/ Admin] Booking History | 2 | 29/11/2024 | 30/11/2024 | Manh |
| 2.3.4.5 | Code Front-end [User] Service Price List | 2 | 1/12/2024 | 2/12/2024 | Manh |
| 2.3.4.6 | Code Front-end [Doctor] Update Doctor Information | 2 | 29/11/2024 | 30/11/2024 | Vy |

| 2.3.4.7 | Code Front-end [Doctor] Reply Rating and Feedback | 2 | 1/12/2024 | 2/12/2024 | Vy |
| --- | --- | --- | --- | --- | --- |
| 2.3.4.8 | Code Front-end [Doctor] Send Prescription to User | 2 | 3/12/2024 | 4/12/2024 | Vy |
| 2.3.4.9 | Code Back-end [Admin] Medicine Management | 3 | 29/11/2024 | 1/12/2024 | Kien |
| 2.3.4.10 | Code Back-end [User / Doctor] Voice Assistant | 4 | 2/12/2024 | 5/12/2024 | Quan |
| 2.3.4.11 | Code Back-end [User] Service Price List | 1 | 2/12/2024 | 2/12/2024 | Kien |
| 2.3.4.12 | Code Back-end [User/ Admin] Booking History | 2 | 3/12/2024 | 4/12/2024 | Kien |
| 2.3.4.13 | Code Back-end [User] Admin Homepage | 2 | 5/12/2024 | 6/12/2024 | Kien |
| 2.3.4.14 | Code Back-end [Doctor] Send Prescription to User | 1 | 7/12/2024 | 7/12/2024 | Kien |
| 2.3.5 | Testing | 1 | 8/12/2024 | 8/12/2024 | All Member |
| 2.3.6 | Fix bugs | 2 | 9/12/2024 | 10/12/2024 | All Member |
| 2.3.7 | Re-testing | 1 | 11/12/2024 | 11/12/2024 | All Member |
| 2.3.8 | Release Sprint 3 | 2 | 12/12/2024 | 13/12/2024 | All Member |

| 2.3.8.1 | Sprint 3 Review Meeting | 1 | 12/12/2024 | 12/12/2024 | All Member |
| --- | --- | --- | --- | --- | --- |
| 2.3.8.2 | Sprint 3 Retrospective | 1 | 13/12/2024 | 13/12/2024 | All Member |
| 3 | Project ‘s meeting | 1 | 14/12/2024 | 14/12/2024 | All Member |
| 4 | Final Release | 1 | 15/12/2024 | 15/12/2024 | All Member |

# Project Schedule

Table 14: Project Schedule

| Defect Prevention |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Sprint 1 |  | Team members |  |
|  | Sprint 2 |  | Team members |  |
|  | Sprint 3 |  | Team members |  |
| Quality Control |  |  |  |  |
|  | Review: Work Product 1 |  | Mentor - Team members |  |
|  | Review: Work Product 2 |  | Mentor - Team members |  |
|  | Review: Work Product 3 |  | Mentor - Team members |  |
| Project Tracking |  |  |  |  |
|  | Project initiation meeting |  | Team members |  |

|  | Sprint Planning Meeting |  | Team members |  |
| --- | --- | --- | --- | --- |
|  | Sprint 1 Review Meeting |  | Team members |  |
|  | Sprint Planning Meeting |  | Team members |  |
|  | Sprint 2 Review Meeting |  | Team members |  |
|  | Sprint Planning Meeting |  | Team members |  |
|  | Sprint 3 Review Meeting |  | Team members |  |
| QA |  |  |  |  |
|  | Final Inspection: Deliverable 1 |  | Mentor - Team members |  |
|  | Final Inspection: Deliverable 2 |  | Mentor - Team members |  |
|  | Final Inspection: Deliverable 3 |  | Mentor - Team members |  |
|  | Baseline audit: Startup |  | Mentor - Team members |  |
|  | Baseline audit: Wrap-up |  | Mentor - Team members |  |

# Resource

Table 15: Resource

| Full name | Role | Salary Rate (USD/hour) |
| --- | --- | --- |
| Quan, Doan Hoang | Scrum Master | 1 |
| Vy, Nguyen Yen | Product Owner | 1 |
| Lich, Huynh Ngoc | Team member | 1 |
| Manh, Vo Van | Team member | 1 |
| Kien, Tran Trung | Team member | 1 |

# Infrastructure

Table 16: Infrastructure

| Work/Product | Purpose | Expected Availability by | Note |
| --- | --- | --- | --- |
| Development Environment |  |  |  |
| Windows 10 or upper | Operating System | Initiation stage |  |
| MySQL | Database management system | Construction Stage |  |
| HTML-CSS, JavaScript | Development languages for Web Front-end and Back-end | Construction Stage |  |
| Java Spring Boot | Development languages for Back-end | Construction Stage |  |
| Other Tools |  |  |  |
| GitHub, GGDrive | Source version control | Definition stage |  |
| Trello | Project Management tool | Initiation stage |  |
| Zoom, Discord | Meeting, Communication | Construction stage |  |

| Figma | Design | Initiation stage |  |
| --- | --- | --- | --- |

# Training Plan

Table 17: Traning Plan

| Training Area | Participants | When Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Technical |  |  |  |
| Java Script | All Member members | 7 days | Mandatory |
| ReactJS | All Member members | 7 days | Mandatory |
| Process |  |  |  |
| Quality system | All Member members | 3 hrs | If already trained |
| Configuration management | All Member members | 3 hrs | If already trained |
| Group review | All Member members | 7 hrs | Mandatory |
| Defect prevention | All Member members | 4 hrs | Mandatory |
| SPC tool | All Member members | 1 hrs | Mandatory |
| Agile methodology | All Member members | 1 hrs | Mandatory |

# Project Organization

# Organization Structure

Table 18: Organization Structure

| Role | Responsibility | Name |
| --- | --- | --- |
| Scrum Master | - Communicate the value of Scrum. - Teach the organization on Scrum to maximize business value. - Preserve the integrity and spirit of the Scrum framework. - Serve as a coach and mentor to members of the Team. | Quan, Doan Hoang |

|  | - Respectfully hold the Team, Product Owners and Stakeholders accountable for their commitments. - Continue to work with the Team and business to find and implement improvements. - As a timekeeper - Helping the team agree on what they can achieve during each development sprint (or another period of time). - Helping the team continuously make progress on the project by making sure each person is working on the right tasks, helping to remove any obstacles to the team member’s progress, and protecting the team from distractions. |  |
| --- | --- | --- |
| Product Owner | - A spokesperson for the customer and needs to represent them. - Gathers manages and prioritizes the product backlog. - Has technical product knowledge or specific domain expertise. - Tracks progress towards the release of a product. | Vy, Nguyen Yen |
| Developer | - Responsible for quality - Responsible for delivering the potentiAll Membery shippable product of the Application each sprint. - Report progress based on the remaining time. - Self-organized - Owns the Sprint backlog | All members |

| Mentor | - Guide on the process. - Monitoring All Member activities of the Team. - Help with anything. - Reviews project documents - Reviews product | Msc. Thuan, Trung Nguyen |
| --- | --- | --- |

# Project Team

Table 19: Project Team

| Full Name | Position |
| --- | --- |
| Msc. Trung, Thuan Nguyen | Mentor |
| Quan, Doan Hoang | Scrum Master, Dev-team |
| Vy, Nguyen Yen | Product Owner; Dev-team |
| Lich, Huynh Ngoc | Dev-team |
| Manh, Vo Van | Dev-team |
| Kien, Tran Trung | Dev-team |

# Communication & Reporting

Table 20: Communication & Reporting

| Audience /Attendees | Topic / Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Scrum Master, Members | Daily meeting | Daily | Face to Face, Discord, Zalo |
| Scrum Master, Members | Sprint Planning Meeting | When starting a sprint | Face to Face, Discord, Zalo |
| Scrum Master, Members, Mentor | Sprint Review Meeting | When finishing a sprint | Face to face |
| Scrum Master, Members | Sprint Retrospective | When the sprint review finish | Face to Face, Discord, Zalo |

| Scrum Master, Members | Individual Meeting | When need | Face to Face, Zalo |
| --- | --- | --- | --- |
| Scrum Master, Members, Mentor | Working report, review problem | Once a week | Face to face |

# Configuration Management

<Refer to the CM plan or insert here the contents of the CM plan as appropriated>

# Security Aspects

- Use HTTPS: Ensure that the website uses a secure connection over HTTPS to protect information transmission.

- Login	Authentication:	Implement	strong	login	authentication	to	prevent unauthorized access to the system.

- User Data Protection: Protects users' personal data by encrypting and processing it securely.

- Periodic Security Testing: Perform periodic security testing to detect and fix security vulnerabilities.

- Security Education: Train the development team on important security elements and create information security awareness.

REFERENCES

| No | Reference item | Issued Date | Source | Note |
| --- | --- | --- | --- | --- |
| 1 | Agile Scrum |  | https://www.atlassian.co m/agile/ |  |
|  |  |  | https://www.cprime.co m/resources/what-is-agi le- what-is-scrum/ |  |
|  |  |  | https://www.agileAll Memberianc e.org/agile1 01/ |  |
|  |  |  | The Scrum Framework by International Scrum Institute |  |

| 2 | Software Standards |  | https://www.nws.noaa.g ov/oh/hrl/developers_do cs/General_So ftware_Standards.pdf |  |
| --- | --- | --- | --- | --- |
|  |  |  | https://standards.ieee.or g/standard/1 2208-2017.html |  |
|  |  |  | https://sw-eng.larc.nasa. gov/ |  |