Sprint Backlog

| Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Sprint Plan Meeting | All member | Done | 4 | 4 | 0 | 4 | 0 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 1 |  | Create Sprint Backlog for Sprint 1All member |  | Done | 10 | 10 | 0 | 10 | 0 | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 2 |  | Create Test Plan for Sprint 1 | Manh, Vy, Quan | Done | 10 | 10 | 0 | 10 | 0 |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 3 | PB01 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 8 | 3 |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 4 | PB01 | Design Database | Lich | Done | 5 | 5 | 0 | 8 | 3 |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 5 | PB01 | Code BE | Kien | Done | 20 | 20 | 0 | 25 | 5 |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 6 | PB01 | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 20 | 5 |  |  |  |  |  |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 7 | PB01 | Test & fix bug | All | Overtimed | 5 | 5 | 0 | 10 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |
| 1, 8 | PB02 | Design UI | Manh, Vy | Done | 1 | 1 | 0 | 1 | 0 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 9 | PB02 | Code BE | Lich | Done | 5 | 5 | 0 | 5 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 10 | PB02 | Code FE | Kien | Done | 3 | 3 | 0 | 3 | 0 |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 11 | PB02 | Test & fix bug | All | Done | 1 | 1 | 0 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |
| 1, 12 | PB06 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 8 | 3 |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 13 | PB06 | Design Database | Lich | Done | 5 | 5 | 0 | 8 | 3 |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 14 | PB06 | Code BE | Quan, Kien | Done | 20 | 20 | 0 | 25 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 15 | PB06 | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 20 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 16 | PB06 | Test & fix bug | All | Done | 3 | 3 | 0 | 5 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |
| 1, 17 | PB05 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 18 | PB05 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 19 | PB05 | Code BE | Quan, Kien | Done | 15 | 15 | 0 | 18 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |  |  |
| 1, 20 | PB05 | Code FE | Manh, Vy | Done | 10 | 10 | 0 | 13 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 21 | PB05 | Test & fix bug | All | Done | 3 | 3 | 0 | 3 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  |
| 1, 22 | PB22 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 23 | PB22 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 24 | PB22 | Code BE | Kien | Done | 20 | 20 | 0 | 20 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |
| 1, 25 | PB22 | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 15 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |  |  |
| 1, 26 | PB22 | Test & fix bug | All | Done | 3 | 3 | 0 | 3 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 27 | PB14 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |
| 1, 28 | PB14 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 29 | PB14 | Code BE | Lich | Done | 20 | 20 | 0 | 21 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |  |  |
| 1, 30 | PB14 | Code FE | Manh, Vy | Done | 15 | 15 | 0 | 16 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |
| 1, 31 | PB14 | Test & fix bug | All | Done | 3 | 3 | 0 | 5 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |
| 1, 32 | PB04 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 33 | PB04 | Design Database | Lich | Done | 5 | 5 | 0 | 5 | 0 |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 34 | PB04 | Code BE | Kien | Done | 25 | 25 | 0 | 30 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25 |  |  |  |
| 1, 35 | PB04 | Code FE | Manh, Vy | Done | 25 | 25 | 0 | 30 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25 |  |  |  |
| 1, 36 | PB04 | Test & fix bug | All | Done | 3 | 3 | 0 | 5 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |
| 1, 37 | PB19 | Design UI | Manh, Vy | Done | 5 | 5 | 0 | 7 | 2 |  |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 38 | PB19 | Design Database | Lich | Done | 5 | 5 | 0 | 10 | 5 |  |  |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1, 39 | PB19 | Code BE | Kien | Overtimed | 30 | 30 | 0 | 35 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 15 |
| 1, 40 | PB19 | Code FE | Manh, Vy | Overtimed | 25 | 25 | 0 | 30 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10 |
| 1, 41 | PB19 | Test & fix bug | All | Overtimed | 3 | 3 | 0 | 10 | 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 1, 42 |  | Sprint review | All member | Done | 4 | 4 | 0 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 |
| 1, 43 |  | Sprint retrospective | All member | Done | 4 | 4 | 0 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 |
| 1, 44 |  | Release & Closing | All member | Done | 2 | 2 | 0 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |
|  |  |  |  | Total | 407 | 407 | 0 | 496 | 89 | 14 | 10 | 11 | 15 | 20 | 15 | 5 | 5 | 0 | 0 | 15 | 23 | 0 | 50 | 4 | 30 | 3 | 35 | 3 | 20 | 3 | 0 | 50 | 3 | 0 | 38 |
|  |  |  |  | Burn down |  |  |  |  |  | 393 | 383 | 372 | 357 | 337 | 322 | 317 | 312 | 312 | 312 | 297 | 274 | 274 | 224 | 220 | 190 | 187 | 152 | 149 | 129 | 126 | 126 | 76 | 73 | 73 | 35 |
|  |  |  |  | Burn up |  |  |  |  |  | 14 | 24 | 35 | 50 | 70 | 85 | 90 | 95 | 95 | 95 | 110 | 133 | 133 | 183 | 187 | 217 | 220 | 255 | 258 | 278 | 281 | 281 | 331 | 334 | 334 | 372 |

Total hours

| Worked hours/Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kien | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 6 | 4 | 4 | 3 | 3 | 3 | 6 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 6 | 6 | 4 | 4 | 4 |
| Lich | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 |
| Quan | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 4 | 4 | 4 | 4 | 4 |
| Vy | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 3 |
| Manh | 4 | 4 | 4 | 3 | 4 | 3 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 4 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 |

105

100

101

90

100

496

Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint

Burn Down Chart

450

400

393 383 372 357337 322 317 312 312 312 297274 274

350

300

250

224 220190 187152 149129 126 126

200

150

100

76 73 73

50

35

0

Day 1

Day 2

Day 3

Day 4

Day 5

Day 6

Day 7

Day 8

Day 9

Day 10

Day 11

Day 12

Day 13

Day 14

Day 15

Day 16

Day 17

Day 18

Day 19

Day 20

Day 21

Day 22

Day 23

Day 24

Day 25

Day 26