## Table 1
Sprint Backlog
| Sprint Id | Backlog Id | Description |  | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26
| 1 |  | Sprint Plan Meeting |  | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 4
| 1, 1 |  | Create Sprint Backlog for Sprint |  | All member | Done | 10 | 10 | 0 | 10 | 0 | Day 1: 10
| 1, 2 |  | Create Test Plan for Sprint 1 |  | Manh, Vy, Quan | Done | 10 | 10 | 0 | 10 | 0 | Day 2: 10
| 1, 3 | PB01 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 8 | 3 | Day 3: 5
| 1, 4 | PB01 | Design Database |  | Lich | Done | 5 | 5 | 0 | 8 | 3 | Day 4: 5
| 1, 5 | PB01 | Code BE |  | Kien | Done | 20 | 20 | 0 | 25 | 5 | Day 12: 20
| 1, 6 | PB01 | Code FE |  | Manh, Vy | Done | 15 | 15 | 0 | 20 | 5 | Day 11: 15
| 1, 7 | PB01 | Test & fix bug |  | All | Overtimed | 5 | 5 | 0 | 10 | 5 | Day 26: 3
| 1, 8 | PB02 | Design UI |  | Manh, Vy | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 3
| 1, 9 | PB02 | Code BE |  | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 14: 5
| 1, 10 | PB02 | Code FE |  | Kien | Done | 3 | 3 | 0 | 3 | 0 | Day 12: 3
| 1, 11 | PB02 | Test & fix bug |  | All | Done | 1 | 1 | 0 | 1 | 0 | bar: Day 15
| 1, 12 | PB06 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 8 | 3 | Day 3: 5
| 1, 13 | PB06 | Design Database |  | Lich | Done | 5 | 5 | 0 | 8 | 3 | Day 4: 5
| 1, 14 | PB06 | Code BE |  | Quan, Kien | Done | 20 | 20 | 0 | 25 | 5 | Day 14: 20
| 1, 15 | PB06 | Code FE |  | Manh, Vy | Done | 15 | 15 | 0 | 20 | 5 | Day 14: 15
| 1, 16 | PB06 | Test & fix bug |  | All | Done | 3 | 3 | 0 | 5 | 2 | Day 15: 3
| 1, 17 | PB05 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 4: 5
| 1, 18 | PB05 | Design Database |  | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 5: 5
| 1, 19 | PB05 | Code BE |  | Quan, Kien | Done | 15 | 15 | 0 | 18 | 3 | Day 16: 15
| 1, 20 | PB05 | Code FE |  | Manh, Vy | Done | 10 | 10 | 0 | 13 | 3 | Day 14: 10
| 1, 21 | PB05 | Test & fix bug |  | All | Done | 3 | 3 | 0 | 3 | 0 | Day 17: 3
| 1, 22 | PB22 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 5: 5
| 1, 23 | PB22 | Design Database |  | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 5: 5
| 1, 24 | PB22 | Code BE |  | Kien | Done | 20 | 20 | 0 | 20 | 0 | Day 18: 20
| 1, 25 | PB22 | Code FE |  | Manh, Vy | Done | 15 | 15 | 0 | 15 | 0 | Day 16: 15
| 1, 26 | PB22 | Test & fix bug |  | All | Done | 3 | 3 | 0 | 3 | 0
| 1, 27 | PB14 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 5: 5; Day 19: 3
| 1, 28 | PB14 | Design Database |  | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 6: 5
| 1, 29 | PB14 | Code BE |  | Lich | Done | 20 | 20 | 0 | 21 | 1 | Day 20: 20
| 1, 30 | PB14 | Code FE |  | Manh, Vy | Done | 15 | 15 | 0 | 16 | 1 | Day 18: 15
| 1, 31 | PB14 | Test & fix bug |  | All | Done | 3 | 3 | 0 | 5 | 2 | Day 21: 3
| 1, 32 | PB04 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 6 | 1 | Day 6: 5
| 1, 33 | PB04 | Design Database |  | Lich | Done | 5 | 5 | 0 | 5 | 0 | Day 6: 5
| 1, 34 | PB04 | Code BE |  | Kien | Done | 25 | 25 | 0 | 30 | 5 | Day 23: 25
| 1, 35 | PB04 | Code FE |  | Manh, Vy | Done | 25 | 25 | 0 | 30 | 5 | Day 23: 25
| 1, 36 | PB04 | Test & fix bug |  | All | Done | 3 | 3 | 0 | 5 | 2 | Day 24: 3
| 1, 37 | PB19 | Design UI |  | Manh, Vy | Done | 5 | 5 | 0 | 7 | 2 | Day 7: 5
| 1, 38 | PB19 | Design Database |  | Lich | Done | 5 | 5 | 0 | 10 | 5 | Day 8: 5
| 1, 39 | PB19 | Code BE |  | Kien | Overtimed | 30 | 30 | 0 | 35 | 5 | Day 26: 15
| 1, 40 | PB19 | Code FE |  | Manh, Vy | Overtimed | 25 | 25 | 0 | 30 | 5 | Day 26: 10
| 1, 41 | PB19 | Test & fix bug |  | All | Overtimed | 3 | 3 | 0 | 10 | 7 | Day 26: 0
| 1, 42 |  | Sprint review |  | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
| 1, 43 |  | Sprint retrospective |  | All member | Done | 4 | 4 | 0 | 4 | 0 | Day 26: 4
| 1, 44 |  | Release & Closing |  | All member | Done | 2 | 2 | 0 | 2 | 0 | Day 26: 2
[6 empty] | Total | 407 | 407 | 0 | 496 | 89 | 14 | 10 | 11 | 15 | 20 | 15 | 5 | 5 | 0 | 0 | 15 | 23 | 0 | 50 | 4 | 30 | 3 | 35 | 3 | 20 | 3 | 0 | 50 | 3 | 0 | 38
[6 empty] | Burn down | [5 empty] | 393 | 383 | 372 | 357 | 337 | 322 | 317 | 312 | 312 | 312 | 297 | 274 | 274 | 224 | 220 | 190 | 187 | 152 | 149 | 129 | 126 | 126 | 76 | 73 | 73 | 35
[6 empty] | Burn up | [5 empty] | 14 | 24 | 35 | 50 | 70 | 85 | 90 | 95 | 95 | 95 | 110 | 133 | 133 | 183 | 187 | 217 | 220 | 255 | 258 | 278 | 281 | 281 | 331 | 334 | 334 | 372
[10 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | Total hours
[10 empty] | Kien |  | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 6 | 4 | 4 | 3 | 3 | 3 | 6 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 6 | 6 | 4 | 4 | 4 | 105
[10 empty] | Lich |  | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 100
[10 empty] | Quan |  | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 101
[10 empty] | Vy |  | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 90
[10 empty] | Manh |  | 4 | 4 | 4 | 3 | 4 | 3 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 5 | 4 | 4 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 100
[10 empty] | Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint | [27 empty] | 496
393 383 372 357
337 322 317 312 312 312
297 274 274
224 220
190 187
152 149 129 126 126
76 73 73
35
Burn Down Chart
450
400
350
300
250
200
150
100
50
0
Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day Day 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26